## WBS with Gantt Chart - BLANK
PROJECT TITLE | MINI-ERP
PROJECT MANAGER | Huỳnh Ngọc Cảnh
COMPANY NAME | SH SOFT VINA
STAGE | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK COMPLETE | REVIEW & SYNTHESIZE | WEEK 1 | [5 empty] | WEEK 2 | [5 empty] | WEEK 3 | [5 empty] | WEEK 4
[8 empty] | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S
REQUIREMENT-DEFINITION | ALL OF AUTH (LOGIN/REGISTER) | THINH | 2023-09-27 | 2023-09-27 | 1 | 100% | CANH | bar: WEEK 1 W
| ALL OF USER | HIEU | 2023-09-27 | 2023-09-27 | 1 | 100% | bar: WEEK 1 W
| ALL OF NOTIFICATION + COMMENT | THINH | 2023-09-28 | 2023-09-28 | 1 | 100% | bar: WEEK 1 T
| ALL OF ACCOUNTING | LAM | 2023-09-28 | 2023-09-28 | 1 | 100% | bar: WEEK 1 T
| ALL OF TIMESHEETS | CANH | 2023-09-28 | 2023-09-28 | 1 | 100% | bar: WEEK 1 T
| ALL OF TASK + COMMENT | CANH | 2023-09-30 | 2023-09-30 | 1 | 100% | bar: WEEK 1 S
| ALL OF SCHEDULE | CANH | 2023-09-30 | 2023-09-30 | 1 | 100% | bar: WEEK 1 S
| ALL OF SETTING | CANH | 2023-09-30 | 2023-09-30 | 1 | 100% | bar: WEEK 1 S
| ALL OF HAPPINESS + GROWTH + ABUNDANCE | CANH | 2023-09-30 |  |  | 20%
DESIGN (PPT) | ALL OF AUTH (LOGIN/REGISTER) | THINH | 2023-10-02 | 2023-10-02 | 1 | 100% | CANH | bar: WEEK 2 M
| ALL OF USER | HIEU | 2023-10-03 | 2023-10-03 | 1 | 100% | bar: WEEK 2 T
| ALL OF NOTIFICATION + COMMENT | THINH | 2023-10-03 | 2023-10-03 | 1 | 100% | bar: WEEK 2 T
| ALL OF ACCOUNTING | LAM | 2023-10-05 | 2023-10-05 | 1 | 100% | bar: WEEK 2 T
| ALL OF TIMESHEETS | CANH | 2023-10-04 | 2023-10-04 | 1 | 100% | bar: WEEK 2 W
| ALL OF TASK + COMMENT | CANH | 2023-10-05 | 2023-10-06 | 2 | 100% | bar: WEEK 2 T to WEEK 2 F
| ALL OF SCHEDULE | CANH | 2023-10-05 | 2023-10-06 | 2 | 100% | bar: WEEK 2 T to WEEK 2 F
| ALL OF SETTING | CANH | 2023-10-05 | 2023-10-06 | 2 | 100% | bar: WEEK 2 T to WEEK 2 F
| ALL OF HAPPINESS + GROWTH + ABUNDANCE | THINH |  |  |  | 0%
DATABASE | DIAGRAM DATABASE & TABLES | CANH | 2023-09-26 |  |  | 80% | CANH | bar: WEEK 1 T to WEEK 3 M
API | [AUTH] LOGIN | CANH |  |  |  | 100% | CANH
| [AUTH] REGISTER USER | THINH |  |  |  | 100%
| [USER] GET USERS (SORT + SEARCH + PAGING, FILTER, ...) | HIEU |  |  |  | 100%
| [USER] GET USER DETAIL | HIEU |  |  |  | 100%
| [USER] UPDATE USER | HIEU |  |  |  | 100%
| [USER] DELETE USER | HIEU |  |  |  | 100%
| [USER] APPROVAL ACCOUNT USER | LAM |  |  |  | 100%
| [USER] GET LIST USERNAME | CANH |  |  |  | 100%
| [CONTRACT] CREATE CONTRACT | CANH |  |  |  | 100%
| [CONTRACT] GET CONTRACT DETAIL | CANH |  |  |  | 100%
| [CONTRACT] UPDATE CONTRACT | CANH |  |  |  | 100%
| [CONTRACT] DELETE CONTRACT | CANH |  |  |  | 100%
| [NOTIFICAITON] GET NOTIFICAITONS (SORT + SEARCH + PAGING, FILTER, ...) | HIEU |  |  |  | 100%
| [NOTIFICAITON] CREATE NOTIFICAITON | HIEU |  |  |  | 100%
| [NOTIFICAITON] UPDATE NOTIFICAITON | HIEU |  |  |  | 100%
| [NOTIFICAITON] DELETE NOTIFICAITON | HIEU |  |  |  | 100%
| [NOTIFICAITON] GET NOTIFICAITON DETAIL | HIEU |  |  |  | 100%
| [COMMENT NOTIFICAITON] COMMENT DETAIL | THINH |  |  |  | 100%
| [COMMENT NOTIFICAITON] CREATE COMMENT | THINH |  |  |  | 100%
| [COMMENT NOTIFICAITON] UPDATE COMMENT | THINH |  |  |  | 100%
| [COMMENT NOTIFICAITON] DELETE COMMENT | THINH |  |  |  | 100%
| [ACCOUNTING] GET LIST MONTH/YEAR | LAM |  |  |  | 100%
| [ACCOUNTING] GET LIST ACCOUTING BY MONTH/YEAR(SORT + SEARCH + PAGING, FILTER, ...) | LAM |  |  |  | 100%
| [ACCOUNTING] CREATE ACCOUNTING | LAM |  |  |  | 100%
| [ACCOUNTING] UPDATE ACCOUNTING | LAM |  |  |  | 100%
| [ACCOUNTING] DELETE ACCOUNTING | LAM |  |  |  | 100%
| [TIMESHEETS] GET LIST ACCOUTING BY MONTH/YEAR(SORT + SEARCH + PAGING, FILTER, ...) | CANH |  |  |  | 100%
| [TIMESHEETS] GET TOTAL WORKING DAY | CANH |  |  |  | 100%
| [TASK] GET LIST TASK (SORT + SEARCH + PAGING, FILTER, ...) | CANH |  |  |  | 100%
| [TASK] REGISTER TASK | CANH |  |  |  | 100%
| [TASK] UPDATE TASK | CANH |  |  |  | 100%
| [TASK] GET STATUS TASK COUNT | CANH |  |  |  | 100%
| [TASK] GET TASK DETAIL | CANH |  |  |  | 100%
| [TASK] DELETE TASK | CANH |  |  |  | 100%
| [TASK] GET TASK BY HASHTAG | CANH |  |  |  | 100%
| [COMMENT TASK] COMMENT DETAIL | HIEU |  |  |  | 100%
| [COMMENT TASK] CREATE COMMENT | HIEU |  |  |  | 100%
| [COMMENT TASK] UPDATE COMMENT | HIEU |  |  |  | 100%
| [COMMENT TASK] DELETE COMMENT | HIEU |  |  |  | 100%
| [WEEKLY REPORT] GET LIST | HIEU |  |  |  | 100%
| [WEEKLY REPORT] GET REPORT DETAIL | HIEU |  |  |  | 100%
| [WEEKLY REPORT]CREATE REPORT | HIEU |  |  |  | 100%
| [HAPPINESS + GROWTH + ABUNDANCE] | LAM, THINH |  |  |  | 20%
| WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION
| 1 | Login/Register |  | 2023-09-25 | 2023-09-27 | 3
API | 1.1 | Common | QUOC THINH | 2023-09-25 | 2023-09-25 | 1 | % of TASK
| 1.2 | Login | QUOC THINH | 2023-09-26 | 2023-09-26 | 1 | COMPLETE | WEEK 1 M: WEEK 1; WEEK 2 M: WEEK 2; WEEK 2 S: WEEK 3; WEEK 3 S: WEEK 4
| 1.3 | Registration | QUOC THINH | 2023-09-27 | 2023-09-27 | 1 |  | M | T | W | R | F | Sat | M | T | W | R | F | M | T | W | R | F | Sat | M | T | W | R | F | Sat
| 1.4 | Check registration from Admin | TUYEN LAM | 2023-09-25 | 2023-09-25 | 1 | 100%
| 1.5 | Role | QUOC THINH | 2023-09-27 | 2023-09-27 | 1 | 100% | bar: WEEK 1 M
| 2 | Human |  | 2023-09-25 | 2023-10-03 | 8 | 100% | bar: WEEK 1 T
| 2.1 | Employee list | TRUNG HIEU | 2023-09-25 | 2023-09-25 | 1 | 100% | bar: WEEK 1 W
| 2.2 | Search in employee list | TRUNG HIEU | 2023-09-25 | 2023-09-25 | 1 | 100% | bar: WEEK 1 M
| 2.3 | Employee information detail | TRUNG HIEU | 2023-09-26 | 2023-09-27 | 2 | bar: WEEK 1 W
| 2.4 | Employee Info edition | TRUNG HIEU | 2023-09-28 | 2023-09-29 | 2 | 100%
| 2.5 | Employee info creation | TRUNG HIEU | 2023-09-29 | 2023-09-30 | 2 | 100% | bar: WEEK 1 M
| 2.6 | Employee deletion | TRUNG HIEU | 2023-09-30 | 2023-10-02 | 2 | 100% | bar: WEEK 1 M
| 2.7 | Employee working time with timekeeping | TRUNG HIEU | 2023-10-03 | 2023-10-03 | 1 | 100% | bar: WEEK 1 T to WEEK 1 W
| 3 | Accounting |  | 2023-09-25 | 2023-09-30 | 6 | 100% | bar: WEEK 1 R to WEEK 1 F
| 3.1 | Transaction list (by Month) | TUYEN LAM | 2023-09-25 | 2023-09-26 | 2 | 100% | bar: WEEK 1 F to WEEK 1 Sat
| 3.2 | Transaction detail | TUYEN LAM | 2023-09-27 | 2023-09-27 | 1 | 100% | bar: WEEK 1 Sat to WEEK 2 M
| 3.3 | Transaction creation | TUYEN LAM | 2023-09-28 | 2023-09-29 | 2 | bar: WEEK 2 T
| 3.4 | Transaction delete | TUYEN LAM | 2023-09-30 | 2023-09-30 | 1 | 100%
| 3.5 | Transaction update | TUYEN LAM | 2023-09-28 | 2023-09-29 | 2 | 100% | bar: WEEK 1 M to WEEK 1 T
| 4 | Notification |  | 2023-09-28 | 2023-10-05 | 7 | 100% | bar: WEEK 1 W
| 4.1 | Notification list | QUOC THINH | 2023-09-28 | 2023-09-29 | 2 | 100% | bar: WEEK 1 R to WEEK 1 F
| 4.2 | Notification detail | QUOC THINH | 2023-09-30 | 2023-09-30 | 1 | 100% | bar: WEEK 1 Sat
| 4.3 | Notification reply | QUOC THINH | 2023-09-30 | 2023-10-02 | 2 | bar: WEEK 1 R to WEEK 1 F
| 4.4 | Notification detail creation | QUOC THINH | 2023-10-03 | 2023-10-04 | 2 | 100%
| 4.5 | Notification detail updation and deletion | QUOC THINH | 2023-10-04 | 2023-10-05 | 2 | 100% | bar: WEEK 1 R to WEEK 1 F
| 4.5 | [5 empty] | 100% | bar: WEEK 1 Sat
| 5 | Task |  | 2023-09-25 | 2023-10-04 | 9 | 100% | bar: WEEK 1 Sat to WEEK 2 M
| 5.1 | Tasks board | NGOC CANH |  |  |  | 100% | bar: WEEK 2 T to WEEK 2 W
| 5.1 | Task Board | NGOC CANH | 2023-09-25 | 2023-09-26 | 2 | 0% | bar: WEEK 2 W to WEEK 2 R
| 5.2 | Status | NGOC CANH | 2023-09-27 | 2023-09-28 | 2
| 5.3 | Priority | NGOC CANH | 2023-09-28 | 2023-09-29 | 2 | 1%
| 5.4 | Search in list board | NGOC CANH | 2023-09-29 | 2023-09-29 | 1 | 100%
| 5.5 | Filter task by status | NGOC CANH |  |  |  | 100% | bar: WEEK 1 M to WEEK 1 T
| 5.5 | Filter task by status | NGOC CANH | 2023-09-30 | 2023-09-30 | 1 | 100% | bar: WEEK 1 W to WEEK 1 R
| 5.6 | Task detail | NGOC CANH | 2023-09-30 | 2023-09-30 | 1 | 100% | bar: WEEK 1 R to WEEK 1 F
| 5.7 | Task detail - Comments | TRUNG HIEU | 2023-10-03 | 2023-10-04 | 2 | 1% | bar: WEEK 1 F
| 5.8 | Task detail creation | NGOC CANH | 2023-10-02 | 2023-10-02 | 1 | 100%
| 5.9 | Task detail/comments updation and deletion | NGOC CANH | 2023-10-03 | 2023-10-04 | 2 | 100% | bar: WEEK 1 Sat
| 5.10 | Weekly report | TRUNG HIEU | 2023-10-05 | 2023-10-06 | 1 | 100% | bar: WEEK 1 Sat
| 5.11 | Weekly report detail | TRUNG HIEU | 2023-10-05 | 2023-10-06 | 1 | 100% | bar: WEEK 2 T to WEEK 2 W
| 6 | Happiness + Growth + Abundance |  | 2023-10-02 |  |  | 100% | bar: WEEK 2 M
| 6.1 | Affirmation | TUYEN LAM | 2023-10-02 |  |  | 100% | bar: WEEK 2 T to WEEK 2 W
| 6.2 | Gratitude | TUYEN LAM | 2023-10-03 |  |  | 100% | bar: WEEK 2 R to WEEK 2 F
| 6.3 | Time management | TUYEN LAM | 2023-10-04 | bar: WEEK 2 R to WEEK 2 F
20%
20% | bar: WEEK 2 M to WEEK 2 R
20% | bar: WEEK 2 M to WEEK 2 R

## WBS with Gantt Chart
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE | MINI-ERP
PROJECT MANAGER | Huỳnh Ngọc Cảnh
COMPANY NAME | SHSOFTVINA
DATE | [6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception & Initiation
1.1 | Project Charter | Leon W | 2022-03-12 | 2022-03-15 | #NAME? | 100%
1.1.1 | Project Charter Revisions | Kylie R | 2022-03-15 | 2022-03-16 | #NAME? | 100%
1.2 | Research | Pete S | 2022-03-15 | 2022-03-21 | #NAME? | 90%
1.3 | Projections | Steve L | 2022-03-16 | 2022-03-22 | #NAME? | 40%
1.4 | Stakeholders | Allen W | 2022-03-17 | 2022-03-22 | #NAME? | 70%
1.5 | Guidelines | Malik M | 2022-03-18 | 2022-03-22 | #NAME? | 60%
1.6 | Project Initiation | Malik M | 2022-03-23 | 2022-03-23 | #NAME? | 20%
2 | Project Definition & Planning
2.1 | Scope & Goal Setting | Steve L | 2022-03-24 | 2022-03-28 | #NAME? | 5%
2.2 | Budget | Allen W | 2022-03-29 | 2022-04-02 | #NAME? | 30%
2.3 | Communication Plan | Malik M |  |  | #NAME? | 0%
2.4 | Risk Management | Malik M |  |  | #NAME? | 0%
3 | Project Launch & Execution
3.1 | Status & Tracking | Pete S |  |  | #NAME? | 0%
3.2 | KPIs | Leon W |  |  | #NAME? | 0%
3.2.1 | Monitoring | Kylie R |  |  | #NAME? | 0%
3.2.2 | Forecasts | Kylie R |  |  | #NAME? | 0%
3.3 | Project Updates | Pete S |  |  | #NAME? | 0%
3.3.1 | Chart Updates | Malik M |  |  | #NAME? | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives | Steve L |  |  | #NAME? | 0%
4.2 | Quality Deliverables | Allen W |  |  | #NAME? | 0%
4.3 | Effort & Cost Tracking | Malik M |  |  | #NAME? | 0%
4.4 | Project Performance | Malik M |  |  | #NAME? | 0%
Formulas:
DURATION = _xludf.DAYS([DUE DATE],[START DATE])